## Iteration 1
Iteration 1
| YES | 30
| NO | 11
| Total | 41
| TASK METRIC | 73.1707
Category | Tasks | Details | Assigned To |  | Completed
Discussion | Group Meeting | Review bootrap function logic | Everyone |  | YES
Teaching | Knowledge Sharing Session | Sharing of technical knowledge | Everyone |  | YES
Design | Design Use Case |  | Everyone |  | YES
Design | ER Diagram |  | Everyone |  | YES
Design | Logical Diagram |  | Everyone |  | YES
Design | Class Diagram |  | Everyone |  | YES
Design | Sequence Diagram |  | Everyone |  | YES
Implementation | Set-up Database |  | Aloysius | Cheryl | YES
Design | Wireframe UI |  | Aloysius | Haseena | YES
Utility Coding | UploadUtility | Store File in virtual memory | Aloysius | Cheryl | NO
Utility Coding | UploadUtility | Check if valid file | Aloysius | Cheryl | NO
Utility Coding | UnzipUtility | Unzip | Aloysius | Cheryl | NO
Entity Coding | Student | Entity Files | Regan | Huiyan | YES
Entity Coding | Course | Entity Files | Aloysius | Cheryl | YES
Entity Coding | Section | Entity Files | Aloysius | Cheryl | YES
Entity Coding | Bid | Entity Files | Regan | Huiyan | YES
Validation Coding | StudentValidation | student.csv Validation | Cheryl | Huiyan | YES
Validation Coding | CourseValidation | course.csv Validation | Huiyan | Regan | YES
Validation Coding | SectionValidation | section.csv Validation | Haseena | Huiyan | YES
Validation Coding | Common Validation | Common Validation | Huiyan | Haseena | YES
Validation Coding | PreRequisiteValidation | prerequisite.csv Validation | Cheryl | Aloysius | YES
Validation Coding | CourseCompletedValidation | course_completed.csv Validation | Huiyan | Regan | YES
Validation Coding | BidValidation | bid.csv Validation | Haseena | Aloysius | YES
Controller Coding | BootstrapController | Call Validation Methods & DAO | Haseena | Huiyan | NO
DAO Coding | BootstrapDAO | add student into database | Haseena | Huiyan | YES
DAO Coding | BootstrapDAO | add course into database | Haseena | Huiyan | NO
DAO Coding | BootstrapDAO | add section into database | Haseena | Huiyan | NO
DAO Coding | BootstrapDAO | add prerequesite into database | Aloysius | Haseena | NO
DAO Coding | BootstrapDAO | add complete_course into database | Cheryl | Haseena | YES
DAO Coding | BootstrapDAO | add bid into database | Haseena | Cheryl | NO
Servlet Coding | BootstrapServlet |  | Cheryl | Huiyan | NO
TestCase | Student Test Case |  | Regan |  | YES
TestCase | Course Test Case |  | Regan |  | YES
TestCase | Section Test Case |  | Regan |  | YES
TestCase | PreRequesite Test Case |  | Regan |  | YES
TestCase | Course Completed Test Case |  | Regan |  | YES
TestCase | Bid Test Case |  | Regan |  | YES
TestCase | Test Code |  | Everyone |  | NO
REVIEW | Function Review | Sharing of how each function works | Everyone |  | NO
Debugging | Debugging Session | Debug ValidateCourse , Course.java | Huiyan | Haseena | YES
Debugging | Debugging Session | Debug ValidateSection, Section.java | Regan | Cheryl | YES

## Iteration 2
Iteration 2
| YES | 20
| NO | 9
| Total | 29
| TASK METRIC | 68.9655
Category | Tasks | Details | Assigned To |  | Completed
Iteration 1 Tasks Carried Over
DAO Coding | BootstrapDAO | Add Section into Database | Cheryl | regan | YES
DAO Coding | BootstrapDAO | add course into database | Haseena | Huiyan | YES
DAO Coding | BootstrapDAO | Add Pre-Requisite into Database | Huiyan | Regan | YES
DAO Coding | BootstrapDAO | Add Bid into Database | Huiyan | Regan | YES
Utility Coding | UploadUtility | Store File in virtual memory | Aloysius | Cheryl | YES
Utility Coding | Upload Utility | Check if file is valid | Cheryl | Aloysius | YES
Utility Coding | Upload Utility | Unzip File | Cheryl | Aloysius | YES
Servlet Coding | Bootstrap Servlet | call bootstrap controller | Cheryl | Huiyan | YES
Controller Coding | BootstrapController | Call validation methods and DAO | Cheryl | Huiyan | NO
Iteration 2 Tasks
| Finalise Documents | Sequence Diagram, Class File, Logical Diagram, Meeting Minutes | Everyone |  | YES
Discussion | Group Meeting | Review Login Functions Logic and Flow | Everyone |  | YES
Teaching | Knowledge Sharing Session | JSP Coding, JDBC | Everyone |  | YES
Controller Coding | BidController | See class diagram | Huiyan | Haseena | NO
DAO Coding | BidDAO | Methods to retrieve from Database | Huiyan | Haseena | YES
Test Code | Test Bootstrap |  | Everyone |  | NO
Debug | Debug | Bug Squashing Session | Regan | Hasseena | NO
Discussion | Function Review |  | Everyone |  | YES
Controller Coding | CourseSectionController | See class diagram | Regan | Haseena | NO
DAO Coding | CourseDAO | Methods to retrieve from Database | Regan | Haseena | NO
DAO Coding | SectionDAO | Methods to retrieve from Database | Regan | Haseena | YES
UI Coding | Login UI | Login UI page wireframe | Aloysius | Haseena | NO
Login Coding | Login Servlet & Page | Login servlet to take in query from login page | Aloysius | Cheryl | YES
Login Coding | Login Controller | Controller to call StudentDAO and AdminDAO | Aloysius | Cheryl | NO
Login Coding | StudentDAO | DAO method to retrieve USERID & PASSWORD from database | Aloysius | Cheryl | YES
Login Coding | AdminDAO | DAO method to retrieve USERID & PASSWORD from database | Aloysius | Cheryl | NO
Controller Coding | StudentController | See class diagram | Regan | Cheryl | YES
DAO Coding | StudentDAO | Methods to retrieve from Database | Regan | Cheryl | YES
Reformat Code | Reformat Code |  | Aloysius | Cheryl | YES
Debug |  | Solve Git de-synced files | Huiyan | Haseena | YES

## Iteration 3
Iteration 3
|  | YES | 57
|  | NO | 5
|  | Total | 62
|  | TASK METRIC | 91.9355
Planned Execution Date | Category | Tasks | Details | Assigned To |  | Completed
Iteration 2 Tasks Carried Over
2016-03-10 | Login Coding | Login page,servlet,Controller | Controller to call StudentDAO and AdminDAO | Aloysius | Cheryl | YES
2016-03-10 | Controller Coding | BootstrapController | Call validation methods and DAO | Cheryl | Huiyan | YES
2016-03-10 | Controller Coding | BidController | See class diagram | Huiyan | Haseena | YES
2016-03-10 | Test Code | Test Bootstrap Function | Test Bootstrap Function | Regan | Haseena | YES
2016-03-10 | Controller Coding | CourseSectionController | See class diagram | Regan | Haseena | YES
2016-03-10 | DAO Coding | CourseDAO | Methods to retrieve from Database | Regan | Haseena | YES
2016-03-10 | Debugging | Debug Bootstrap | Debug Bootstrap |  |  | YES
2016-05-10 | Login Coding | AdminDAO | DAO method to retrieve USERID & PASSWORD from database | Aloysius | Cheryl | YES
Iteration 3 Tasks
2016-03-10 | Test Case | Search Sections Test Case | Search Sections Test Case | Cheryl |  | YES
2016-03-10 | Test Case | Login Test Case | Login Test Case | Haseena |  | YES
2016-03-10 | Test Case | Add Bid Test Case | Add Bid Test Case | Cheryl |  | YES
2016-03-10 | Test Case | Drop Bid Test Case | Drop Bid Test Case | Cheryl |  | YES
2016-03-10 | Test Case | Update Bid Test Case | Update Bid Test Case | Cheryl |  | YES
2016-03-10 | Test Case | Drop Section Test Case | Drop Section Test Case | Cheryl |  | YES
2016-04-10 | Student Coding | Student Homepage | Student view page (populate display: bids, enrolled classes, round info, student details) | Aloysius | Huiyan | YES
2016-04-10 | Add Bid Coding | Add Bid Servlet | rmb to check min. bid value | Cheryl | Aloysius | YES
2016-05-10 | Student Coding | Student Servlet | Student servlet to take in query from homepage | Regan | Haseena | YES
2016-05-10 | Review | Supervisor Consultation | Supervisor Consultation | Aloysius | Huiyan | YES
2016-05-10 | Drop Bid Coding | Drop Bid Servlet | Handle input from <view> and response from <controller> | Aloysius | Huiyan | YES
2016-05-10 | Admin Coding | Admin Homepage | Admin view page (bootstrap, start round, end round) | All | All | YES
2016-05-10 | Admin Coding | Admin Servlet | Admin servlet to take in query from homepage | Cheryl | Haseena | YES
2016-07-10 | Drop Section Coding | Drop Section Servlet | Handle input from <view> and response from <controller> | Cheryl | Haseena | YES
2016-07-10 | CourseCompleteDAO,SectionStudentDAO | CourseCompleteDAO,SectionStudentDAO | CourseCompleteDAO,SectionStudentDAO | Cheryl | Regan | YES
2016-08-10 | Deployment | Deployment to AWS | Deployment of Login into AWS |  |  | YES
2016-08-10 | Add Bid Coding | Search Sections View Page | Search Sections View Page | Aloysius | Cheryl | YES
2016-08-10 | Student Coding | Student Homepage | Student view page (Add Bid, Drop Bid, Drop Section, Update Bid) | Aloysius | Cheryl | YES
2016-08-10 | Admin Coding | Admin Servlet | Takes in start round query calls RoundController method to start/stop | Cheryl | Regan | YES
2016-08-10 | Student Coding | Student Servlet | Student servlet-handle update bids | Regan | Aloysius | YES
2016-08-10 | Discussion | Group Meeting | Review Admin Functions Logic and Flow,PM Issues | All | All | YES
2016-08-10 | Round Coding | Start/Stop Round | Update status in the database | Aloysius | Cheryl | YES
2016-08-10 | Round Coding | RoundController | Calls RoundDAO to update Round Status to <Started/Ended> | Cheryl | Regan | YES
2016-08-10 | Round Coding | BidDAO | SQL select statement from database determine clearing price for the specific section | Cheryl | Haseena | YES
2016-08-10 | Round Coding | BidDAO | Update Bid <Status> in Database | Cheryl | Haseena | YES
2016-08-10 | Round Coding | RoundController | Calls StudentController refund unsuccessful bids | Cheryl | Regan | YES
2016-08-10 | Round Coding | RoundController | Update to call necessary DAO methods | Cheryl | Aloysius | YES
2016-08-10 | Round Coding | BidController | Compute Min Bid | Aloysius | Cheryl | YES
2016-08-10 | Review | Review | Sharing on how the function works, the coding | All | All | YES
2016-09-10 | Debug | Debug Bootstrap | Debug Bootstrap (After Testing the function) | Cheryl | Hasseena | YES
2016-09-10 | Debug | Debug | Debug-Debug Student functions | Cheryl | Haseena | YES
2016-10-10 | Restructure | Restructure Round 2 Clearing Logic | Restructured clearing logic, however debugging is carried forward | Cheryl | Haseena | NO
2016-10-10 | Deployment | Deployment to AWS | Debugging of Deployment | Cheryl | Aloysius | YES
2016-11-10 | Review | In Class Review | Presentations & Demo preparation | All | All | YES
2016-11-10 | JavaDocs | JavaDocs | JavaDocs Bootstrap Validation | Regan | Haseena | YES
2016-11-10 | JavaDocs | JavaDocs | JavaDocs Controller | Regan | Haseena | YES
2016-11-10 | JavaDocs | JavaDocs | JavaDocs DAO | Regan | Haseena | YES
2016-11-10 | JavaDocs | JavaDocs | JavaDocs Entity | Regan | Haseena | YES
2016-12-10 | CLEARING LOGIC(END ROUND 2) | LiveBid.jsp (View) | Display Rank, Bid, Bid status | Huiyan | Aloysius | NO
2016-12-10 | Student Coding | Student View Completed Course Page | Student View Completed Course Page | Huiyan | Aloysius | YES
2016-12-10 | Test Case | Test Case | Test Round 1 clearing logic | Haseena |  | YES
2016-12-10 | Test Case | Test Case | Test Round 2 clearing logic | Haseena |  | YES
2016-12-10 | Test Case | Test Case | Round 2 Real Time Updates | Haseena |  | YES
2016-12-10 | Test Case | Test Case | Min bid amount logic | Haseena |  | NO
13/10/2016 | Review | Admin Function Review | Sharing on how the function works, the coding | Everyone |  | YES
13/10/2016 | Test Code | Test Code | Run Add Bid Test Case | Cheryl | Huiyan | YES
13/10/2016 | Debug | Debugging Session | Bug Squashing Session | Regan | Aloysius | YES
14/10/2016 | Integration | Integrate | Integrate round bidding and clearing logic with UI | All | All | NO
14/10/2016 | Round Coding | Clear Round | Round clearing-split start and stop, transfer successful bids to sectionstudent | Regan | Cheryl | YES
15/10/2016 | Student Coding | SearchSectionViewPage | Update Search Section page | Cheryl | Aloysius | YES
15/10/2016 | Student Coding | Student Coding | Student view results page | Regan | Aloysius | YES
16/10/2016 | Test Code | Test Code | Run Drop Bid, Drop Section, Search Bid TestCases | Cheryl | Huiyan | YES
16/10/2016 | Programming | CLEARING LOGIC(END ROUND 2) | Alter SQL, JSP tables, Bidding page to show round 2 information | Regan | Aloysius | YES
2016-10-16 | Programming | UI | Create Homepage UI | Cheryl | Aloysius | NO

## Iteration 4
Iteration 4
|  | YES | 25
|  | NO | 3
|  | Total | 28
|  | TASK METRIC | 89.2857
Planned Execution Date | Category | Tasks | Details | Assigned To |  | Completed
Iteration 3 Tasks Carried Over
10/28/2016 | Test Case | Test Case | Min bid amount logic | Haseena |  | YES
10/27/2016 | Integration | Integrate | Integrate round bidding and clearing logic with UI | Cheryl | Aloysius | YES
10/18/2016 | Debugging | Debugging | Debug Iteration 3 bugs | Huiyan | Aloysius | YES
10/18/2016 | UI | UI Coding | UI Coding(Carried over from Iteration 3) | Huiyan | Aloysius | NO
Iteration 4 Tasks
10/17/2016 | Meeting | Knowledge Sharing Session in JSON | Knowledge Sharing Session on JSON | Regan |  | YES
10/17/2016 | Test Case | Test Case JSON | Test Case JSON | Huiyan |  | YES
10/18/2016 | JSON | JSONAuthenticate | JSONAuthenticate | Cheryl | Regan | YES
10/22/2016 | Deployment | AWS Deployment and Debugging | AWS Deployment and Debugging | Cheryl | Regan | YES
10/22/2016 | JSON | JSONBootstrap | JSONBootstrap | Aloysius | Regan | YES
10/22/2016 | JSON | JSONUpdateBid | JSONUpdateBid | Cheryl | Haseena | YES
10/23/2016 | JSON | JSONDeleteBid | JSONDeleteBid | Regan | Haseena | YES
10/23/2016 | JSON | JSONDropSection | JSONDropSection | Regan | Haseena | YES
10/23/2016 | JSON | JSONStartRound | JSONStartRound | Huiyan | Regan | YES
10/23/2016 | JSON | JSONStopRound | JSONStopRound | Haseena | Regan | YES
10/25/2016 | JSON | JSONCommonValidation | JSONCommonValidation | Haseena | Aloysius | YES
10/25/2016 | JSON | JSONDumpBid | JSONDumpBid | Cheryl | Aloysius | YES
10/25/2016 | JSON | JSONDumpSection | JSONDumpSection | Cheryl | Aloysius | YES
10/25/2016 | JSON | JSONDumpTable | JSONDumpTable | Cheryl | Aloysius | YES
10/25/2016 | JSON | JSONDumpUser | JSONDumpUser | Huiyan | Regan | YES
10/25/2016 | Testing | Test Function on AWS | Test Function on AWS | Aloysius | Regan | YES
10/25/2016 | JSON | JSON | Debug JSON | Haseena | Aloysius | NO
10/26/2016 | Deployment | AWS Deployment and Debugging | AWS Deployment and Debugging | Aloysius | Huiyan | YES
10/26/2016 | Debug | Debugging Session | Bug Squashing Session | Aloysius | Regan | YES
10/26/2016 | Debug | Code Cleanup | Code Cleanup | Aloysius | Cheryl | NO
10/26/2016 | Milestone | Supervisor Meeting 2 | Supervisor Meeting 2 | Regan |  | YES
10/26/2016 | Testing | Test Code JSON | Test Code JSON | Huiyan | Haseena | YES
10/28/2016 | Debugging | Debug Buffer Time | Debug Buffer Time | Everyone |  | YES
10/28/2016 | Review | JSON Function Review | JSON Function Review | Cheryl | Huiyan | YES

## Iteration 5
Iteration 5
|  | YES | 9
|  | NO | 5
|  | Total | 14
|  | TASK METRIC | 64.2857
Planned Execution Date | Category | Tasks | Details | Assigned To |  | Completed
Iteration 4 Tasks Carried Over
2016-02-11 | UI | UI Coding | Admin UI Coding | Regan | Haseena | YES
2016-02-11 | UI | UI Coding | Student UI Coding | Huiyan | Haseena | YES
2016-02-11 | JSON | JSON | Debug JSON | Haseena | Aloysius | YES
Iteration 5 Tasks
10/31/2016 | AWS | AWS Deployment | UAT AWS Deployment | Huiyan |  | YES
11/01/2016 | UAT | UAT | User Acceptance Test | Huiyan |  | YES
11/02/2016 | Debug | Debug UAT | Debug UAT manual test bugs | Huiyan | Haseena | YES
11/03/2016 | Javadoc | Javadoc | Create Javadoc | Huiyan | Regan | YES
11/03/2016 | Json Test | JSON | Run Json Test Case | Haseena |  | YES
11/05/2016 | UI Test | UI Test | Create UI Test Case | Cheryl |  | YES
11/02/2016 | Regression Test | Regression Test | Regression Testing Session 1 | Regan | Haseena | NO
11/03/2016 | Debug | Debug Test Case | Debug Regression Testing Session 1 | Regan | Huiyan | NO
11/02/2016 | Regression Test | Regression Test | Regression Testing Session 2 | Aloysius |  | NO
11/03/2016 | Debug | Debug Test Case | Debug Regression Testing Session 2 | Regan | Haseena | NO
11/06/2016 | Debug | Debug UAT | Debug UAT JSON bugs | Regan | Huiyan | NO

## Iteration 6
Iteration 6
|  | YES | 15
|  | NO | 2
|  | Total | 17
|  | TASK METRIC | 88.2353
Planned Execution Date | Category | Tasks | Details | Assigned To |  | Completed
Iteration 5 Tasks Carried Over
11/06/2016 | Debug | Debug UAT | Debug UAT JSON bugs | Regan | Huiyan | YES
11/08/2016 | Regression Test | Regression Test | Regression Testing Session 1 | Regan |  | YES
11/08/2016 | Debug | Debug Test Case | Debug Regression Testing Session 1 | Regan | Huiyan | YES
11/10/2016 | Regression Test | Regression Test | Regression Testing Session 2 | Aloysius |  | YES
11/10/2016 | Debug | Debug Test Case | Debug Regression Testing Session 2 | Regan | Haseena | YES
Iteration 6 Tasks
11/08/2016 | Debug | Debug UI |  | Regan | Haseena | YES
11/08/2016 | Test Case | Create Bid Status Test Case |  | Haseena |  | YES
11/08/2016 | JSONBidStatus | Code JSONBidStatus |  | Huiyan | Aloysius | YES
11/09/2016 | Test | Test JSONBidStatus |  | Huiyan |  | YES
11/09/2016 | Debug | Debug JSONBidStatus |  | Cheryl | Regan | YES
11/10/2016 | Deploy | Deploy and test AWS |  | Regan |  | YES
11/10/2016 | Debug | Debug AWS |  | Cheryl | Haseena | NO
11/11/2016 | Meeting | Group Meeting | Function Review | Cheryl |  | YES
11/10/2016 | Diagram | Update Diagrams |  | Cheryl |  | YES
11/12/2016 | Milestone | Project Submission |  | Cheryl |  | YES
11/13/2016 | Diagram | Documentation & CleanUp |  | Haseena | Aloysius | YES
11/17/2016 | Milestone | Final Presentation |  | Cheryl |  | NO