## Slide 1: Demo & Progress Update (G2T6)

## Slide 2: Demo
Functions:
Add Bid
Drop Bid
Data Used
amy.ng.2019 - qwerty128
Admin - 1234

## Slide 3: Team Progress Update
Project Milestone Reached:
  Complete Student Functionality
  Admin Functionality
  (Iter3) Planned- 75%
  Actual- 69.13%:
(Iter2)Planned–72.48%
Actual - 81.21%

## Slide 4: Progress Update (Based on In-Class Review & Supervisor Meeting 1)
Upload all task on Git schedule
Fixed Git directory
Completed all diagrams

## Slide 5: Team Progress Updates
Git Commit error
  Accidentally commit non-project file into git.
Reshuffle Project Managers
Restructuring of Schedules

## Slide 6: Updated PM Management
Iteration | PM
1 (2 weeks) | Regan & Aloysius
2 (1 week) | Aloysius
3 (2 weeks) | Haseena
4 (2 weeks) | Regan
5 (1 week) | Huiyan
6 (1 week) | Cheryl
The expected completion date: 26/ Oct
Buffer days to UAT: 6 days

## Slide 7: Problems Identified & Mitigations (Task Metric)
P: Over-estimated tasks in iter 2.
M: Balance load factor for future iteration (1 week duration)
P:A lot of micro-planning of small tasks in schedule
M: Re-structure schedule to re-allocate task according to functionality

## Slide 8: Task Metric 2 (Carried over from Iteration 1)
Category | Tasks | Details | Assigned To | Assigned To | Completed
DAO Coding | BootstrapDAO | Add Section into Database | Cheryl | regan | YES
DAO Coding | BootstrapDAO | Add course into database | Haseena | Huiyan | YES
DAO Coding | BootstrapDAO | Add Pre-Requisite into Database | Huiyan | Regan | YES
DAO Coding | BootstrapDAO | Add Bid into Database | Huiyan | Regan | YES
Utility Coding | UploadUtility | Store File in virtual memory | Aloysius | Cheryl | YES
Utility Coding | Upload Utility | Check if file is valid | Cheryl | Aloysius | YES
Utility Coding | Upload Utility | Unzip File | Cheryl | Aloysius | YES
Servlet Coding | Bootstrap Servlet | Call bootstrap controller | Cheryl | Huiyan | YES
Controller Coding | BootstrapController | Call validation methods and DAO | Cheryl | Huiyan | YES

## Slide 9
Category | Tasks | Details | Assigned To | Assigned To | Completed
Discussion | Finalise Documents | Sequence Diagram, Class File, Logical Diagram, Meeting Minutes | Everyone | Everyone | YES
Discussion | Group Meeting | Review Login Functions Logic and Flow | Everyone | Everyone | YES
Teaching | Knowledge Sharing Session | JSP Coding, JDBC | Everyone | Everyone | YES
Controller Coding | BidController | See class diagram | Huiyan | Haseena | NO
DAO Coding | BidDAO | Methods to retrieve from Database | Huiyan | Haseena | YES
Test Code | Test Bootstrap |  | Everyone |  | YES
Task Metric 2

## Slide 10
Category | Tasks | Details | Assigned To | Assigned To | Completed
Debug | Debug | Bug Squashing Session | Regan | Haseena | NO
Discussion | Function Review | Function Review | Everyone | Everyone | YES
Controller Coding | CourseSectionController | See class diagram | Regan | Haseena | NO
DAO Coding | SectionDAO | Methods to retrieve from Database | Regan | Haseena | YES
UI Coding | Login UI | Login UI page wireframe | Aloysius | Haseena | NO
Login Coding | Login Servlet & Page | Login servlet to take in query from login page | Aloysius | Cheryl | YES
Login Coding | Login Controller | Controller to call StudentDAO and AdminDAO | Aloysius | Cheryl | NO
Login Coding | StudentDAO | DAO method to retrieve USERID & PASSWORD from database | Aloysius | Cheryl | YES
Task Metric 2

## Slide 11: Iteration 2 Task Metric
Scheduled Task:
Non Programming : 5
Programming : 22
Actual Completed Task:
Non Programming : 4 / 5
Programming : 15/ 22
Task Metric Score: 68.96%

## Slide 12
Task Metric 3 (Carried over from Iteration 2)
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
3/10/2016 | Login Coding | Login page,servlet,Controller | Controller to call StudentDAO and AdminDAO | Aloysius | Cheryl | YES
3/10/2016 | Controller Coding | BootstrapController | Call validation methods and DAO | Cheryl | Huiyan | YES
3/10/2016 | Controller Coding | BidController | See class diagram | Huiyan | Haseena | YES
3/10/2016 | Test Code | Test Bootstrap Function |  | All | All | YES
3/10/2016 | Controller Coding | CourseSectionController | See class diagram | Regan | Haseena | YES
3/10/2016 | DAO Coding | CourseDAO | Methods to retrieve from Database | Regan | Haseena | YES
5/10/2016 | Login Coding | AdminDAO | DAO method to retrieve USERID & PASSWORD from database | Aloysius | Cheryl | YES

## Slide 13
Task Metric (Iteration 3)
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
3/10/2016 | Test Case | Search Sections Test Case | Search Sections Test Case | Cheryl |  | NO
3/10/2016 | Test Case | Login Test Case | Login Test Case | Haseena |  | YES
3/10/2016 | Test Case | Add Bid Test Case | Add Bid Test Case | Haseena |  | NO
3/10/2016 | Test Case | Drop Bid Test Case | Drop Bid Test Case | Haseena |  | NO
3/10/2016 | Test Case | Update Bid Test Case | Update Bid Test Case | Cheryl |  | NO
3/10/2016 | Test Case | Drop Section Test Case | Drop Section Test Case | Cheryl |  | NO
4/10/2016 | UI Coding | Create HomePage UI | Homepage UI page wireframe | Aloysius | Huiyan | NO

## Slide 14
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
4/10/2016 | Student Coding | Student Homepage | Student view page (populate display: bids, enrolled classes, round info, student details) | Aloysius | Huiyan | YES
4/10/2016 | Add Bid Coding | Add Bid Servlet | rmb to check min. bid value | Cheryl | Aloysius | YES
5/10/2016 | Student Coding | Student Servlet | Student servlet to take in query from homepage | Regan | Haseena | YES
5/10/2016 | Review | Supervisor Consultation | Supervisor Consultation | Aloysius | Huiyan | YES
5/10/2016 | Drop Bid Coding | Drop Bid Servlet | Handle input from <view> and response from <controller> | Aloysius | Huiyan | YES
5/10/2016 | Admin Coding | Admin Homepage | Admin view page (bootstrap, start round, end round) | All | All | YES
Task Metric (Iteration 3)

## Slide 15
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
5/10/2016 | Admin Coding | Admin Servlet | Admin servlet to take in query from homepage | Cheryl | Haseena | YES
7/10/2016 | Drop Section Coding | Drop Section Servlet | Handle input from <view> and response from <controller> | Cheryl | Haseena | YES
7/10/2016 | CourseCompleteDAO,SectionStudentDAO | CourseCompleteDAO,SectionStudentDAO | CourseCompleteDAO,SectionStudentDAO | Cheryl | Regan | YES
8/10/2016 | Deployment | Deployment to AWS | Deployment of Login into AWS |  |  | YES
8/10/2016 | Deployment | Deployment to AWS | Debugging of Deployment |  |  | YES
8/10/2016 | Add Bid Coding | Search Sections View Page | Search Sections View Page | Aloysius | Cheryl | YES
Task Metric (Iteration 3)

## Slide 16
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
8/10/2016 | Student Coding | Student Homepage | Student view page (Add Bid, Drop Bid, Drop Section, Update Bid) | Aloysius | Cheryl | YES
8/10/2016 | Admin Coding | Admin Servlet | Takes in start round query calls RoundController method to start/stop | Cheryl | Regan | YES
8/10/2016 | Student Coding | Student Servlet | Student servlet-handle update bids | Regan | Aloysius | YES
8/10/2016 | Discussion | Group Meeting | Review Admin Functions Logic and Flow,PM Issues | All | All | YES
8/10/2016 | UI Coding | HomePage UI | Homepage UI page wireframe | Haseena | Aloysius | NO
8/10/2016 | Round Coding | Start/Stop Round | Update status in the database | Aloysius | Cheryl | YES
Task Metric (Iteration 3)

## Slide 17
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
8/10/2016 | Round Coding | RoundController | Calls RoundDAO to update Round Status to <Started/Ended> | Cheryl | Regan | YES
8/10/2016 | Round Coding | BidDAO | SQL select statement from database determine clearing price for the specific section | Cheryl | Haseena | YES
8/10/2016 | Round Coding | BidDAO | Update Bid <Status> in Database | Cheryl | Haseena | YES
8/10/2016 | Round Coding | RoundController | Calls StudentController refund unsuccessful bids | Cheryl | Regan | YES
8/10/2016 | Round Coding | RoundController | Update to call necessary DAO methods | Cheryl | Aloysius | YES
Task Metric (Iteration 3)

## Slide 18
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
8/10/2016 | Round Coding | BidController | Compute Min Bid | Aloysius | Cheryl | YES
8/10/2016 | Review | Review | Sharing on how the function works, the coding | All | All | YES
9/10/2016 | Debug | Debug Bootstrap | Debug Bootstrap (After Testing the function) | Cheryl | Hasseena | YES
9/10/2016 | Debug | Debug | Debug-Debug Student functions | Cheryl | Haseena | YES
11/10/2016 | Review | In Class Review | Presentations & Demo preparation | All | All | YES
11/10/2016 | JavaDocs | JavaDocs | JavaDocs Bootstrap Validation | Cheryl | Haseena | YES
Task Metric (Iteration 3)

## Slide 19
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
12/10/2016 | CLEARING LOGIC(END ROUND 2) | LiveBid.jsp (View) | Display Rank, Bid, Bid status | Huiyan | Regan | NO
12/10/2016 | CLEARING LOGIC(END ROUND 2) | LiveBid Servlet | Calls BidController retrieve Bids by specific section | Huiyan | Regan | NO
12/10/2016 | Test Case | Test Case | Test Round 1 clearing logic | Haseena |  | NO
12/10/2016 | Test Case | Test Case | Test Round 2 clearing logic | Haseena |  | NO
Task Metric (In Progress: Iteration 3)

## Slide 20
Date | Category | Tasks | Details | Assigned To | Assigned To | Completed
12/10/2016 | Test Case | Test Case | Round 2 Real Time Updates | Haseena |  | NO
12/10/2016 | Test Case | Test Case | Min bid amount logic | Haseena |  | NO
13/10/2016 | Review | Review | Sharing on how the function works, the coding | Everyone |  | NO
13/10/2016 | Test Code | Test Code | Test code for clearing logic | All | All | NO
13/10/2016 | Debug | Debugginf Session | Bug Squashing Session | Regan | Aloysius | NO
14/10/2016 | Integration | Integrate | Integrate round bidding and clearing logic with UI | All | All | NO
Task Metric (In Progress: Iteration 3)
As of now, Task Metrics: 74.46%

## Slide 21: Pair Programming Metric
Task | Planned | Actual | PPI(%) | Status
Login Page - servlet, controller, page | 2.5 | 2.68 | 93% | OK
CourseDAO | 0.5 | 0.72 | 69% | OK
CourseSection Controller | 1 | 0.92 | 109% | OK
Bootstrap Contoller | 1 | 1.27 | 79% | OK
Bid Controller | 3 | 3.3 | 91% | OK
Debug Bootstrap | 3 | 2.4 | 125% | OK
Add Bid Servlet | 1.5 | 3.47 | 43% | Under-estimated
Student view page(populate display:bids, enrolled classes, round info student details) | 3 | 2.33 | 129% | OK
Student servlet to take in query from homepage | 3 | 3 | 100% | OK
Admin Homepage-Admin Viewpage(boostrap, start round,end round) | 0.5 | 0.55 | 91% | OK

## Slide 22: Pair Programming Metric
Task | Planned | Actual | PPI(%) | Status
AdminDAO retrieve userid and password | 0.5 | 0.6 | 83% | OK
Admin Servlet-Admin servlet to take in query from homepage | 0.5 | 0.42 | 119% | OK
CourseCompleteDAO,SectionStudentDAO | 0.5 | 0.73 | 68% | OK
Drop Section Servlet-handle Input from <view> and response from controller | 0.5 | 1.6 | 31% | Under-estimated
BidDAO-sql Select stamtent from database to detrmine clearing price for specific section | 1 | 1.23 | 81% | OK
Student Servlet-handle update bids | 1 | 1.33 | 75% | OK
RoundDAO-Update ROund Status in Databse to started/ended | 0.5 | 0.53 | 94% | OK

## Slide 23: Pair Programming Metric
Task | Planned | Actual | PPI(%) | Status
RoundController calls ROundDAO to update round status to strated/ended | 0.5 | 0.53 | 94% | OK
Admin Servlet- takes in start round query, calls roundController method to start/stop | 0.5 | 0.98 | 51% | OK
BidDAO- Update Bid status in database | 1 | 1.17 | 85% | OK
Search Sections View page | 2.5 | 2.93 | 85% | OK
RoundController calls StudentController ,refund unsuccessful bids | 1.5 | 1.58 | 95% | OK
Debug- Debug Student Functions |  |  |  | 
JavaDocs - DAO | 1.5 | 1.55 | 97% | OK

## Slide 24: Problem Identified & Mitigation
Take note of under-estimated tasks under the function and taken note to extend time for next task.

## Slide 25: Test Plan
TestNo | Date | Category | Functionality | Description | Done by
1 | 8-10-2016 | Test Case Implementation | 2.1 Bootstrap Upload | Check the functionality of uploading different types of files (zip,rar,etc) | Cheryl & Haseena
2 | 8-8-2016 | Test Case Implementation | Student validation | Successfully updated the student table, if the validation of the various fields and their respective logic is successful | Cheryl & Haseena
3 | 8-8-2016 | Test Case Implementation | Common validation | Check the various files for common errors such as extra whitespaces, columns,rows | Cheryl & Haseena

## Slide 26: Test Plan
TestNo | Date | Category | Functionality | Description | Done by
4 | 8-10-2016 | Test Case Implementation | Course Validation | Successfully updated the course table, if the validation of the various fields and their respective logic is successful | Cheryl & Haseena
5 | 8-10-2016 | Test Case Implementation | Course completed validation | Successfully updated the course completed table, if the validation of the various fields and their respective logic is successful | Cheryl & Haseena

## Slide 27: Test Plan
TestNo | Date | Category | Functionality | Description | Done by
6 | 8-10-2016 | Test Case Implementation | Prerequisite validation | Successfully updated the prerequisite table, if the validation of the various fields and their respective logic is successful | Cheryl & Haseena
7 | 8-10-2016 | Test Case Implementation | Section validation | Successfully updated the section table, if the validation of the various fields and their respective logic is successful | Cheryl & Haseena

## Slide 28
TestNo | Date | Category | Functionality | Description
8 | 8-10-2016 | Test Case Implementation | Bid validation | Successfully updated the bid table, if the validation of the various fields and their respective logic is successful
Test Plan

## Slide 29: Iter 2-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
27/09/2016 | ValidateBid | check bid amt is more than $10 | 5 | High | Code Integration | 5
Added Debug Session to Schedule : End of Iteration

## Slide 30: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
3/10/2016 | Bootstrap Controller | Encounter server error when running the read files | 5 | High | Code Integration | 5
3/10/2016 | CourseSection Controller | getCoursesByCourseTitle() -> change name to getCoursesContainingTitle return type from course to arrayList<Course> // to return courses with similar name as input | 5 | High | Code Integration | 10
3/10/2016 | CourseDAO | getCoursesByCourseTitle() -> change name to getCoursesContainingTItle return type from course to arrayList<Course> change SQL statement from equals to like | 5 | High | Code Integration | 15
Added Debug Session to Schedule : Bug Metric reached >15

## Slide 31: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
5/10/2016 | BidController | Change the return type for deleteBid() from double to boolean. | 5 | High | Code Integration | 5
8/10/2016 | CourseDAO | getCourseContainingTitle cause sql exception | 5 | High | Code Integration | 10
8/10/2016 | SectionDAO | getSectionByCourseCode never add sections into arrayList | 5 | High | Code Integration | 15
8/10/2016 | BidDAO | AddBid set String wrongly | 5 | High | Code Integration | 20
Added Debug Session to Schedule : Bug Metric reached >20.

## Slide 32: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
10/08/2016 | CommonValidation | Database Field: “amy.ng.2015” still contains extra spaces | 5 | High | Commonvalidation:Test Case 1 | 5
10/08/2016 | CommonValidation | Subsequent rows not read after an error entry was encountered | 5 | High | Commonvalidation:Test Case 2 | 10
10/08/2016 | CommonValidation | Empty row was processed and shown in error list as all blank fields | 5 | High | Commonvalidation:Test Case 3 | 15
Added Debug Session to Schedule : Bug Metric reached >15.

## Slide 33: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
8-Oct | ValidateCourse | Course with exam end time after exam start time was added into the database | 5 | High | Course Validation: Test Case 5 | 5
8-Oct | ValidateCourse | Course with description field exceeding 1000 characters was added in the database | 5 | High | Course Validation: Test Case 7 | 10
8-Oct | ValidateCourse | Course with course code field exceeding 10 characters correctly validated, however there was no error message shown | 5 | High | Course Validation: Test Case 8 | 15
Added Debug Session to Schedule : Bug Metric reached >15.

## Slide 34: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
8-Oct | ValidateSection | Section has venue which clashes with another section having another lesson at the same timeslot and venue | 5 | High | SectionValidation: Test Case 10 | 5
8-Oct | ValidateStudent | Student with edollar containing more than 2 decimal places was added into the database | 5 | High | StudentValidation:Test Case 6 | 10
8-Oct | ValidateStudent | Existing student with edollar at 9999 was not added into the database, however it should have logged an existing userId error | 5 | High | StudentValidation: Test Case 10 | 15
8-Oct | BootStrapController | Zip file with only 1 csv file was uploaded and the program crashed instead of displaying an error message | 5 | High | BootStrap_UploadTestCase: 2 | 20

## Slide 35: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
8-Oct | BidValidation | Displayed invalid userid, invalid section, not own school course, class timetable clash. Happened after invalid userid that was not found in student.csv was entered into bid.csv | 5 | High | BidValidationTestCase 1 | 25
8-Oct | BidValidation | Displayed invalid amount, invalid section, class timetable clash. Happened after negative bid amount was entered into bid.csv | 5 | High | BidValidationTestCase 2 | 30
8-Oct | BidValidation | Displayed invalid amount, invalid section, class timetable clash. Happened after amount with more than 2 decimals places was entered into bid.csv | 5 | High | BidValidationTestCase 3 | 35

## Slide 36: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
8-Oct | BidValidation | Displayed invalid amount, invalid section, class timetable clash. Happened after amount with more than 2 decimals places was entered into bid.csv | 5 | High | BidValidationTestCase 4 | 40
8-Oct | BidValidation | Displayed invalid code, not own school course, class timetable clash. Happened after a course code that was found in course.csv into bid.csv | 5 | High | BidValidationTestCase 5 | 45
8-Oct | BidValidation | Displayed not own school course, class timetable clash. Happened after a bid for a module form SOB was made in round 1 by a student from SIS | 5 | High | BidValidationTestCase 6 | 50

## Slide 37: Iter 3-Bug Metrics
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
8-Oct | BidValidation | Student was not able to bid for IS101 although she completed IS100 which is a prerequisite of IS101 | 5 | High | BidValidationTestCase 10 | 55
8-Oct | BidValidation | Was not able to add any new courses | 5 | High | BidValidationTestCase 12 | 60
8-Oct | BidValidation | Was not able to add any new courses | 5 | High | BidValidationTestCase 13 | 65
8-Oct | BidValidation | Empty row error did not appear | 5 | High | BidValidationTestCase 14 | 70

## Slide 38: Mitigation Steps
-Have a buffer time included in the task schedule so that opportunity risk of bugs are reduced outside PP session.
-Set the top 2 stronger coder in the team to review the code before pushing.
-Set the task according to the pair’s strengths.