## Slide 1: Supervisor Meeting 2
G2-T6
Last Updated: 25th Oct 2016

## Slide 2: Overview
Progress
Team Progress Update
Milestone
Problems Identified & Mitigation Actions
Metrics
Demo

## Slide 3: Progress
Iteration 3 – Ended on 16 October 2016
91.94 % of tasks completed
Completed All Functions except for JSON and UI

## Slide 4: Progress
Milestone
Milestone | Week | Project Manager (PM)
Supervisor Meeting 1 | 5-6 | Regan (PM1) Aloysius (PM2)
PM Review | 7 | Aloysius
In class Review | 8-9 | Haseena
Supervisor Meeting 2 | 10-11 | Regan
User Acceptance Test | 12 | Huiyan
Project Submission | 14 | Cheryl
Final Presentation | 14 | Cheryl

## Slide 5: Progress
Project Manager Schedule
Iteration | Week | Project Manager (PM)
1 | 5-6 | Regan (PM1) Aloysius (PM2)
2 | 7 | Aloysius
3 | 8-9 | Haseena
4 | 10-11 | Regan
5 | 12 | Huiyan
6 | 13-14 | Cheryl

## Slide 6: Progress
Iteration 4 – In Progress
JSON
S/N | Task | Status
 | JSONAuthenticate | Completed
2. | JSONBootstrap | Not Completed
3. | JSONUpdateBid | Not Completed
4. | JSONDeleteBid | Completed
5. | JSONDropSection | Completed
6. | JSONStartRound | Not Completed
7. | JSONStopRound | Not Completed

## Slide 7: Progress
Iteration 4 – In Progress
JSON
S/N | Task | Status
8. | JSONCommonValidation | Not Completed
9. | JSONDumpBid | Not Completed
10. | JSONDumpSection | Not Completed
11. | JSONDumpTable | Not Completed
12. | JSONDumpUser | Not Completed

## Slide 8: Progress UPdate
7 Days Behind Schedule
Planned completion date: 26th Oct
Expected completion date: 30th Oct
Causes
Much of the team was busy preparing for the Lab Test and completing other assignments

## Slide 9: Progress Update
Mitigation Actions
Dedicate more hours and complete more tasks near the end of the iteration
Everyone is able to dedicate slightly more hours for this iteration at this period
Utilize the buffer days(2) allocated to Iteration 4

## Slide 10: MileStone
Iteration 5
Buffer day (1)
User Acceptance Test (1 Nov 2016)
Follow-up actions following results of UAT

## Slide 11: MileStone
Iteration 6
Buffer Days(6)
Project Submission
Final Presentation

## Slide 12: Problems Identified & Mitigation
Link during Application Demo was not the right instance
Cause
We used appDebug instead of app as we used our backup copy(clone app)
Mitigation
Remember to use correct instance for UAT

## Slide 13: Metrics
Task Metrics(Iteration 3)
Scheduled Task:
Non Programming : 15
Programming : 47
Total: 62
Actual Completed Task:
Non Programming : 14 /15
Programming : 43/ 47
Total: 57/62
Iteration 3 : 57/62 Tasks Completed 91.94% Task Completion Rate
Vast Improvement over 68.97% achieved in Iteration 2
`
`

## Slide 14: Metrics
Task Metrics(Iteration 4)
Scheduled Task:
Non Programming : 5
Programming : 22
Total : 27
Actual Completed Task:
Non Programming : 0/5
Programming : 5/22
Total 5/27
Tasks still in Progress. Iteration 4 ends on 30 Oct 2016
Many of the tasks are actually partially done as we broke down the tasks into smaller parts
`
`

## Slide 15: Tasks Metric(From iter 3)
Category | Tasks | Details | Assigned To | Assigned To | Completed
Debug | Debug Bootstrap | Debug Bootstrap (After Testing the function) | Cheryl | Hasseena | YES
Debug | Debug | Debug-Debug Student functions | Cheryl | Haseena | YES
Restructure | Restructure Round 2 Clearing Logic | Restructured clearing logic, however debugging is carried forward | Cheryl | Haseena | NO
Deployment | Deployment to AWS | Debugging of Deployment | Cheryl | Aloysius | YES
Review | In Class Review | Presentations & Demo preparation | All | All | YES
JavaDocs | JavaDocs | JavaDocs Bootstrap Validation | Regan | Haseena | YES
JavaDocs | JavaDocs | JavaDocs Controller | Regan | Haseena | YES

## Slide 16: Tasks Metric(From iter 3)
Category | Tasks | Details | Assigned To | Assigned To | Completed
JavaDocs | JavaDocs | JavaDocs Entity | Regan | Haseena | YES
CLEARING LOGIC(END ROUND 2) | LiveBid.jsp (View) | Display Rank, Bid, Bid status | Huiyan | Aloysius | NO
Student Coding | Student View Completed Course Page | Student View Completed Course Page | Huiyan | Aloysius | YES
Test Case | Test Case | Test Round 1 clearing logic | Haseena |  | YES
Test Case | Test Case | Test Round 2 clearing logic | Haseena |  | YES
Test Case | Test Case | Round 2 Real Time Updates | Haseena |  | YES
Test Case | Test Case | Min bid amount logic | Haseena |  | NO

## Slide 17: Tasks Metric(From iter 3)
Category | Tasks | Details | Assigned To | Assigned To | Completed
Review | Admin Function Review | Sharing on how the function works, the coding | Everyone |  | YES
Test Code | Test Code | Run Add Bid Test Case | Cheryl | Huiyan | YES
Debug | Debugging Session | Bug Squashing Session | Regan | Aloysius | YES
Integration | Integrate | Integrate round bidding and clearing logic with UI | All | All | NO
Round Coding | Clear Round | Round clearing-split start and stop, transfer successful bids to sectionstudent | Regan | Cheryl | YES
Student Coding | SearchSectionViewPage | Update Search Section page | Cheryl | Aloysius | YES
Student Coding | Student Coding | Student view results page | Regan | Aloysius | YES

## Slide 18: Tasks Metric(From iter 3)
Category | Tasks | Details | Assigned To | Assigned To | Completed
Test Code | Test Code | Run Drop Bid, Drop Section, Search Bid TestCases | Cheryl | Huiyan | YES
Programming | CLEARING LOGIC(END ROUND 2) | Alter SQL, JSP tables, Bidding page to show round 2 information | Regan | Aloysius | YES
Programming | UI | Create Homepage UI | Cheryl | Aloysius | NO

## Slide 19: Tasks Metric(Carried over from ITEr 3)
Category | Tasks | Details | Assigned To | Assigned To | Completed
Test Case | Test Case | Min bid amount logic | Haseena |  | NO
Integration | Integrate | Integrate round bidding and clearing logic with UI | Cheryl | Aloysius | NO
Debugging | Search Sections Test Case | Debug Iteration 3 bugs | Huiyan | Aloysius | NO
UI | UI Coding | UI Coding(Carried over from Iteration 3) | Huiyan | Aloysius | NO

## Slide 20: Tasks Metric(Current iter)
Category | Tasks | Details | Assigned To | Assigned To | Completed
Meeting | Knowledge Sharing Session in JSON | Knowledge Sharing Session on JSON | Regan |  | NO
Test Case | Test Case JSON | Test Case JSON | Huiyan |  | NO
JSON | JSONAuthenticate | JSONAuthenticate(Done but pplog down) | Cheryl | Regan | NO
Deployment | AWS Deployment and Debugging | AWS Deployment and Debugging | Cheryl | Regan | NO
JSON | JSONBootstrap | JSONBootstrap | Aloysius | Regan | NO
JSON | JSONUpdateBid | JSONUpdateBid | Cheryl | Haseena | NO
JSON | JSONDeleteBid | JSONDeleteBid | Regan | Haseena | YES

## Slide 21: Tasks Metric(Current iter)
Category | Tasks | Details | Assigned To | Assigned To | Completed
JSON | JSONDropSection | JSONDropSection | Regan | Haseena | YES
JSON | JSONStartRound | JSONStartRound | Huiyan | Regan | NO
JSON | JSONStopRound | JSONStopRound | Haseena | Regan | NO
JSON | JSONCommonValidation | JSONCommonValidation | Haseena | Aloysius | YES
JSON | JSONDumpBid | JSONDumpBid | Cheryl | Aloysius | NO
JSON | JSONDumpSection | JSONDumpSection | Cheryl | Aloysius | NO
JSON | JSONDumpTable | JSONDumpTable | Cheryl | Aloysius | NO

## Slide 22: Tasks Metric(Current iter)
Category | Tasks | Details | Assigned To | Assigned To | Completed
JSON | JSONDumpUser | JSONDumpUser | Huiyan | Regan | NO
Testing | Test Function on AWS | Test Function on AWS | Aloysius | Regan | NO
Deployment | AWS Deployment and Debugging | AWS Deployment and Debugging | Aloysius | Huiyan | NO
Debug | Debugging Session | Bug Squashing Session | Aloysius | Regan | NO
Debug | Code Cleanup | Code Cleanup | Aloysius | Cheryl | NO
Milestone | Supervisor Meeting 2 | Supervisor Meeting 2 | Regan |  | NO
Testing | Test Code JSON | Test Code JSON | Huiyan | Haseena | NO

## Slide 23: Tasks Metric(Current iter)
Category | Tasks | Details | Assigned To | Assigned To | Completed
JSON | JSONDumpUser | JSONDumpUser | Huiyan | Regan | NO
Testing | Test Function on AWS | Test Function on AWS | Aloysius | Regan | NO
Deployment | AWS Deployment and Debugging | AWS Deployment and Debugging | Aloysius | Huiyan | NO
Debug | Debugging Session | Bug Squashing Session | Aloysius | Regan | NO
Debug | Code Cleanup | Code Cleanup | Aloysius | Cheryl | NO
Milestone | Supervisor Meeting 2 | Supervisor Meeting 2 | Regan |  | NO
Testing | Test Code JSON | Test Code JSON | Huiyan | Haseena | NO

## Slide 24: Tasks Metric(Current iter)
Category | Tasks | Details | Assigned To | Assigned To | Completed
Debugging | Debug Buffer Time | Debug Buffer Time | Everyone |  | NO
Review | JSON Function Review | JSON Function Review | Cheryl | Huiyan | NO

## Slide 25: Task Metric
Current Iteration task completion rate may look low
However, a lot of the iteration’s tasks are partially completed as we have segregated individual tasks into multiple pair programming sessions

## Slide 26: Pair Programming Metrics(From iter 3)
Task | Planned | Actual | PPI(%) | Status
JavaDocs-Entity | 0.5 | 0.8 | 63% | OK
Debugging Session | 4 | 4.38 | 91% | OK
Split start and stop button | 1 | 1.3 | 77% | OK
student view results page | 1 | 1.3 | 77% | OK
Update search section page | 1 | 1.37 | 73% | OK

## Slide 27: Pair Programming Metrics(From Iter 3)
Task | Planned | Actual | PPI(%) | Status
Alter SQL, JSP tables, Bidding page to show round 2 information | 1 | 1.65 | 61% | OK
JavaDocs - BootStrap Validation | 1.5 | 1.47 | 102% | OK
Create HomePage UI | 1 | 1.53 | 65% | OK
Student View Completed Course Page | 0.5 | 0.45 | 111% | OK

## Slide 28: Pair Programming Metrics(Current Iter)
Task | Planned | Actual | PPI(%) | Status
Debug Iteration 3 Bugs | 2 | 2.85 | 70% | OK
JSONAuthentication | 2 | 2.37 | 84% | OK
JSON DumpTable | 1.5 | 1.4 | 107% | OK
JSON DumpTable | 1.25 | 1.25 | 100% | OK
JSONDeleteBid | 2 | 1.88 | 106% | OK

## Slide 29: Pair Programming Metrics(Current Iter)
Task | Planned | Actual | PPI(%) | Status
JSONDropSection | 2 | 1.8 | 111% | OK
JSONDumpTable | 0.75 | 1.2 | 63% | OK
JSONStopRound | 2 | 1.73 | 116% | OK
AWS Deployment and Debugging | 1 | 1.08 | 93% | OK
JSON Common Validation Class | 1 | 0.65 | 154% | Over-estimated

## Slide 30: Pair Programming Metrics(Current Iter)
Task | Planned | Actual | PPI(%) | Status
JSONDropSection | 0.5 | 0.37 | 135% | OK
JSONCommonValidation Class | 0.5 | 0.78 | 64% | OK
JSON DeleteBid | 0.5 | 0.7 | 71% | OK

## Slide 31: Metrics
Bug Metrics
Total Bug Score: 187
Current Bug Score: 0
Total Bugs found since Demo : 11
Status: All Resolved

## Slide 32: Bug Metrics Bug breakdown
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
14/10/2016 | BidValidation | Bids are subtracted from student edollar twice | Low | 1 | None(Found during debug) | 1
14/10/2016 | SectionStudentController | Cannot drop section | High | 5 | None(Found during debug) | 6
15/10/2016 | BidController | Able to bid for completed course | High | 5 | None(Found while doing javadocs) | 5
15/10/2016 | ValidateStudent | Student's eDollar did not check if it is more than 3 decimal places | High | 5 | None(Found while doing javadocs) | 10
16/10/2016 | AddBidServlet | Able to add a bid during inactive round | High | 5 | AddBidTestCase 15 | 5

## Slide 33
Date Found | File With Bug | Changes | Bug Value | Impact | Test Case/ Code Integration | Total
16/10/2016 | searchSection | Was not able to add decimal bid amount | High | 5 | AddBidTestCase 16 | 5
16/10/2016 | BidController | Bid section limit doesn’t include enrolled sections | High | 5 | AddBidTestCase 17 | 10
16/10/2016 | BidController | Able to bid fro section already enrolled in | High | 5 | AddBidTestCase 18 | 15
16/10/2016 | SearchSection | Shows a blank page when searching for section under course that doesn't contain sections | High | 5 | SearchTestCase 5 | 20
18/10/2016 | StudentHome | The second and the following successful bids are out of the enrolment table | Low | 1 | Round1TestCase3 | 25
18/10/2016 | BidDAO | 2 bids at the clearing price can be bidded successfully with only 1 available slot | High | 5 | Round1TestCase5 | 26
Bug Metrics Bug breakdown

## Slide 34: MisTakes Made
S/N | Mistake | Description
1 | Accidentally started task | Noticed that it was just a half an hour task and decided to just go ahead with it
2 | Accidentally clicked stop iteration button | Immediately emailed Paul and Rajesh to report about the violation and thereafter, resumed the iteration

## Slide 35
Thank you