## Slide 1: Supervisor Meeting
G2-T6

## Slide 2: Overview

## Slide 3: Project Manager Schedule
Iteration | Week | Project Manager (PM)
1 | 5-6 | Regan (PM1) Aloysius (PM2)
2 | 7 | Aloysius
3 | 8-9 | Cheryl
4 | 10-11 | Huiyan
5 | 12 | Haseena

## Slide 4: Project Milestones
Milestone | Week | Project Manager (PM)
Supervisor Meeting 1 | 6 (PM 2) | Aloysius
Project Manager Review | 7 | Aloysius
In Class Review | 9 | Cheryl
Supervisor Meeting 2 | 11 | Huiyan
User Acceptance Test | 12 | Haseena
Project Submission | 13 | Regan
Final Presentation | 14 | Regan

## Slide 5: Project Development Sequence
Iteration 1
Iteration 2
Bootstrapping
Login
Validation
Database Input
Controller
DAOs
Iteration 3 / 4
Admin Functionality
Student Functionality
Web Service
Iteration 5
UAT Mitigation
Buffer Coding TIme
File Upload

## Slide 6: Iteration Format
General meeting
Teaching/Sharing session
PP Coding
Test Case Creation
Testing
Function Review
Team meeting to discuss what are to be done in the following week
Prior to session, PM will allocate a specific aspect to research on and share findings
Testing of code against corner case and test case. Bugs are to be noted down.
Explanation of code done by PP pairs, and sharing of rational behind coding ideology.

## Slide 7: Iteration 1 Overall Breakdown :
Iteration | 1
Duration | 2 weeks
Date | 12/09/16 - 18/09/16
Project Manager | Regan
Coding Pair 1 | Cheryl, Aloysius
Coding Pair 2 | Haseena, Huiyan
Date | 19/09/16 - 25/09/16
Project Manager | Aloysius
Coding Pair 1 | Cheryl, Regan
Coding Pair 2 | Haseena, Huiyan
Work Hours | 
Regan | 21
Aloysius | 23
Cheryl | 23
Huiyan | 22.5

## Slide 8: Iteration 1 : Schedule

## Slide 9: Iteration 1 : Schedule

## Slide 10: Iteration 2
Note: Anticipating some carry-over task to be completed on Monday

## Slide 11: Project Schedule Status (on-going)
Behind time: 9 hours

## Slide 12: Tracking

## Slide 13: Pair Programming Hours Metrics (Iteration 1)
Task | Planned Hours | Actual Hours | PPM | Action
Create Course Entity | 1 | 0.67 | 1.50 | No action required
Create Student Entity | 1 | 1.1 | 0.91 | No action required
Create Section Entity | 1 | 1.17 | 0.86 | No action required
Validate course.csv | 3 | 2.92 | 1.03 | No action required
Create Bid Entity | 1 | 3.07 | 0.33 | For future task, PM must be informed about the start/end and duration of task before starting.
PPM | Action
0.5-1.5 | No action required
<0.5 | Re-estimate Review issues
>1.5 | Re-estimate Review issues

## Slide 14
Task | Planned Hours | Actual Hours | PPM | Action
Validate student.csv | 3.0 | 2.63 | 1.14 | No action required
Setup database | 2 | 2.43 | 0.82 | No action required
Validate Prerequisite.csv | 4 | 2.5 | 1.60 | Re-estimate buffer time for coding sessions (Reduce)
Do common validations for all csv files | 1 | 0.97 | 1.03 | No action required
Validate Section.csv | 3.5 | 2.3 | 1.52 | Re-estimate buffer time for coding sessions (Reduce)
Validate Courses Completed.csv | 4 | 4.13 | 0.97 | No action required
Pair Programming Hours Metrics (Iteration 1)

## Slide 15: Bugs / Incident Documents
Bugs Tracking (For Project Member’s reference)
Incident Tracking (Learning points: serve as reminder of possible mistakes)

## Slide 16: PPLog
Prerequisite Validation
Prerequisite Validation
Create Bid Entity

## Slide 17: Schedule Metrics
Iteration | Planned Hours | Actual Hours | Score | Status
1 | 47.5 | ~28 | <Pending> | On-going
2 | 29 | - | - | Not Started
3 | 40 | - | - | Not Started
4 | 30 | - | - | Not Started
5 (UAT Week) | Tentative | - | - | Tentative

## Slide 18: Issues

## Slide 19: Issues
Schedule
  Overestimated the task
  Over-optimistic about clocking hours resulting in shifting to another dates.
PP-log Incidents
  Forget to click complete button once we stop the task
  Not familiar with PP-log
  Metrics not showing correct information
Git Incidents
  Pushing of code outside of session. (Reason: adding in checking of corner case)

## Slide 20: Mitigation Plans

## Slide 21: Mitigation Plans
Schedule
  Use current coding speed/hours to benchmark future iterations. Changes to future iteration are made.
  Identify high complexity tasks and allocate over reasonable timeframe (over two days or over a few task sessions)
  Back-up plan when team members are not able to commit to planned coding session/date.
PP-log
  For future tasks, PM must be informed about the start/end and duration of task before start.
  PP-log to be checked by all team members regularly. PM to check in on pplog when programming pair inform PM that their session is done.

## Slide 22: Questions for Supervisor
Can we have numbers in name ? (Do we make assumptions?)
Can we assume the schools are SMU faculties, ie. SIS, SOE, SOSS, SOA
Do we need to include web service in the use case/logical diagram
What can we push into GIT , non-programming tasks, database?, test cases, minutes.
Are we allowed to make code changes to completed tasks (to correct coding errors)?

## Slide 23
End of Slides