## Iteration1
Bug Metric Iteration 1: 11/09/2016-25/09/2016
No. | Date Found | File | Details | Impact level | Bug Value | Current Value | Date Resolved | No. of Test Cases | Found by? | Note | Status
1 | 14/09/2016 | BootstrapController | change HashMap<String,String> to HashMap<String, ArrayList<String>> for courseComplete | High | 5 | 5 | 14/09/2016 | 0/0 | Huiyan | Found during PP Session | Resolved
2 | 17/09/2016 | SQL create table statements | change NULL to NOT NULL | Low | 1 | 6 | 24/09/2016 | 0/0 | Cheryl | Found during PP Session | Resolved
3 | 17/09/2016 | BootstrapController | change HashMap<String,String> to HashMap<String, ArrayList<String>> for pre-Req | High | 5 | 11 | 17/09/2016 | 0/0 | Aloysius | Found during PP Session | Resolved
4 | 18/09/2016 | ValidateSection | line 67: isValidInstructor change to isValidVenue | Low | 1 | 1 | 24/09/2016 | 0/0 | Huiyan/Haseena | Found during PP Session | Resolved
5 | 24/09/2016 | ValidateSection | change input type from ArrayList<String> to ArrayList<Section> | High | 5 | 6 | 24/09/2016 | 0/0 | Aloysius | Found during PP Session | Resolved
6 | 24/09/2016 | BootstrapController | change SECTIONLIST to Hashmap <String, ArrayList<Section>> | High | 5 | 11 | 24/09/2016 | 0/0 | Huiyan | Found during PP Session | Resolved
7 | 24/09/2016 | ValidateSection | change SECTIONLIST to STUDENTSECTION | Low | 1 | 1 | 24/09/2016 | 0/0 | Aloysius | Found during PP Session | Resolved
8 | 24/09/2016 | ValidateCourse | change return type for isValidDateFormat from boolean to date | Low | 1 | 2 | 25/09/2016 | 0/0 | Huiyan | Found during PP Session | Resolved
9 | 24/09/2016 | Course | change all datatype for the dates from String to Date | High | 5 | 7 | 25/09/2016 | 0/0 | Huiyan | Found during PP Session | Resolved
10 | 27/09/2016 | ValidateBid | check bid amt is more than $10 | Low | 1 |  |  | 0/0 | Cheryl | Found during PP Session | Resolved
Formula=1 x num (low) + 5 x num (high) + 10 x num (critical)
|  | Severity | Description |  |  |  |  | Current Bug Points | 0 | `
|  | Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues. |  |  |  |  | Total Bug Points | 29
|  | High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
|  | Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue. |  |  |  | Symbols
= Stop development and begin debug session
= used the planned debugging tme in the iteration

## Iteration2
Iteration 2: 27/10/2016-02/10/2016
| Date Found | File | Details | Impact level | Bug Value | Current Value | Date Resolved | No. of Test Cases | Found by? | Note | Status
10 | 27/09/2016 | ValidateBid | check bid amt is more than $10 | High | 5 | 5 | 28/10/2016 | 0/0 | Cheryl | Found during PP Session | Resolved
Current Bug Point | 0
Total Bug Point | 5
Symbols
= Stop development and begin debug session
= used the planned debugging tme in the iteration
Formula=1 x num (low) + 5 x num (high) + 10 x num (critical)
| Severity | Description
| Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
| High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
| Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.

## Iteration3
Iteration 3: 3/10/2016-16/10/2016
| Date Found | File | Details | Impact level | Bug Value | Current Value | Date Resolved | Test Case/ Code Integration | Found by? | Note | Status
1 | 2016-10-03 | BootstrapController | encounter server error when running the read files | High | 5 | 5 | 2016-10-06 | Code Integration | Cheryl/Huiyan | Found during PP Session | Resolved
2 | 2016-10-03 | CourseSectionController | getCoursesByCourseTitle() -> change name to getCoursesContainingTitle return type from course to arrayList<Course> // to return courses with similar name as input | High | 5 | 10 | 2016-10-06 | Code Integration | Cheryl | While reviewing code and class diagram | Resolved
3 | 2016-10-03 | CourseDAO | getCoursesByCourseTitle() -> change name to getCoursesContainingTItle return type from course to arrayList<Course> change SQL statement from equals to like | High | 5 | 15 | 2016-10-06 | Code Integration | Cheryl | While reviewing code and class diagram | Resolved
4 | 2016-10-05 | BidController | Change the return type for deleteBid() from double to boolean. | High | 5 | 5 | 2016-10-08 | Code Integration | Cheryl | Found while attempting to figure out student controller | Resolved
5 | 2016-10-05 | CourseDAO | getCourseContainingTitle cause sql exception | High | 5 | 10 | 2016-10-08 | Code Integration | Huiyan | Found during PP Session | Resolved
6 | 2016-10-05 | SectionDAO | getSectionByCourseCode never add sections into arrayList | High | 5 | 15 | 2016-10-08 | Code Integration | Huiyan | Found during PP Session | Resolved
7 | 2016-10-05 | BidDAO | AddBid set String wrongly | High | 5 | 20 | 2016-10-08 | Code Integration | Huiyan | Found during PP Session | Resolved
8 | 2016-10-08 | CommonValidation | Database Field: “amy.ng.2015” still contains extra spaces | High | 5 | 10 | 2016-10-10 | Commonvalidation:Test Case 1 | Haseena | Function Testing Session | Resolved
9 | 2016-10-08 | CommonValidation | Subsequent rows not read after an error entry was encountered | High | 5 | 15 | 2016-10-10 | Commonvalidation:Test Case 2 | Haseena | Function Testing Session | Resolved
10 | 2016-10-08 | CommonValidation | Empty row was processed and shown in error list as all blank fields | High | 5 | 20 | 2016-10-10 | Commonvalidation:Test Case 3 | Haseena | Function Testing Session | Resolved
11 | 2016-10-08 | ValidateCourse | Course with exam end time after exam start time was added into the database | High | 5 | 5 | 2016-10-11 | Course Validation: Test Case 5 | Haseena | Function Testing Session | Resolved
12 | 2016-10-08 | ValidateCourse | Course with description field exceeding 1000 characters was added in the database | High | 5 | 10 | 2016-10-11 | Course Validation: Test Case 7 | Haseena | Function Testing Session | Resolved
13 | 2016-10-08 | ValidateCourse | Course with course code field exceeding 10 characters correctly validated, however there was no error message shown | High | 5 | 15 | 2016-10-11 | Course Validation: Test Case 8 | Haseena | Function Testing Session | Resolved
14 | 2016-10-08 | ValidateSection | Section has venue which clashes with another section having another lesson at the same timeslot and venue | High | 5 | 5 | 2016-10-11 | SectionValidation: Test Case 10 | Haseena | Function Testing Session | Resolved
15 | 2016-10-08 | ValidateStudent | Student with edollar containing more than 2 decimal places was added into the database | High | 5 | 10 | 2016-10-11 | StudentValidation:Test Case 6 | Haseena | Function Testing Session | Resolved | It is okay to have more than 2 dp, if data will truncate to 2dp
16 | 2016-10-08 | ValidateStudent | Existing student with edollar at 9999 was not added into the database, however it should have logged an existing userId error | High | 5 | 15 | 2016-10-11 | StudentValidation: Test Case 10 | Haseena | Function Testing Session | Resolved
17 | 2016-10-08 | ValidateStudent | Student name with exactly 100 chars was not added into the database | High | 5 | 20 | 2016-10-11 | StudentValidation: Test Case 13 | Haseena | Function Testing Session | Resolved
18 | 2016-10-08 | BootStrapController | Zip file with only 1 csv file was uploaded and the program crashed instead of displaying an error message | High | 5 | 25 | 2016-10-11 | BootStrap_UploadTestCase: 2 | Haseena | Function Testing Session | Resolved
19 | 2016-10-08 | BidValidation | Displayed invalid userid, invalid section, not own school course, class timetable clash. Happened after invalid userid that was not found in student.csv was entered into bid.csv | High | 5 | 5 | 14/11/2016 | BidValidationTestCase 1 | Haseena | Function Testing Session | Resolved | Incorrect Test Data - same as above
20 | 2016-10-08 | BidValidation | Displayed invalid amount, invalid section, class timetable clash. Happened after negative bid amount was entered into bid.csv | High | 5 | 10 | 14/11/2016 | BidValidationTestCase 2 | Haseena | Function Testing Session | Resolved | Incorrect Test Data - same as above
21 | 2016-10-08 | BidValidation | Displayed invalid amount, invalid section, class timetable clash. Happened after amount with value below 10 was entered into bid.csv | High | 5 | 15 | 14/11/2016 | BidValidationTestCase 3 | Haseena | Function Testing Session | Resolved | Incorrect Test Data - same as above
22 | 2016-10-08 | BidValidation | Displayed invalid amount, invalid section, class timetable clash. Happened after amount with more than 2 decimals places was entered into bid.csv | High | 5 | 20 | 14/11/2016 | BidValidationTestCase 4 | Haseena | Function Testing Session | Resolved | Incorrect Test Data - same as above
23 | 2016-10-08 | BidValidation | Displayed invalid code, not own school course, class timetable clash. Happened after a course code that was found in course.csv into bid.csv | High | 5 | 25 | 15/11/2016 | BidValidationTestCase 5 | Haseena | Function Testing Session | Resolved | Incorrect Test Data - same as above
24 | 2016-10-08 | BidValidation | Displayed not own school course, class timetable clash. Happened after a bid for a module form SOB was made in round 1 by a student from SIS | High | 5 | 30 | 15/11/2016 | BidValidationTestCase 6 | Haseena | Function Testing Session | Resolved | Incorrect Test Data - same as above
25 | 2016-10-08 | BidValidation | Student was not able to bid for IS101 although she completed IS100 which is a prerequisite of IS101 | High | 5 | 35 | 15/11/2016 | BidValidationTestCase 10 | Haseena | Function Testing Session | Resolved
26 | 2016-10-08 | BidValidation | Was not able to add any new courses | High | 5 | 40 | 15/11/2016 | BidValidationTestCase 12 | Haseena | Function Testing Session | Resolved
27 | 2016-10-08 | BidValidation | Was not able to add any new courses | High | 5 | 45 | 15/11/2016 | BidValidationTestCase 13 | Haseena | Function Testing Session | Resolved
28 | 2016-10-08 | BidValidation | Empty row error did not appear | High | 5 | 50 | 15/11/2016 | BidValidationTestCase 14 | Haseena | Function Testing Session | Resolved
29 | 14/8/2016 | BidValidation | Bids are subtracted from student edollar twice | Low | 1 | 1 | 15/11/2016 | None | Aloysius | Found during debug | Resolved
30 | 14/8/2016 | SectionStudentController | Cannot drop section | High | 5 | 6 | 15/11/2016 | None | Aloysius | Found during debug | Resolved
31 | 15/10/2016 | BidController | Able to bid for completed course | High | 5 | 5 | 15/11/2016 | None | Haseena | Found while doing javaDocs | Resolved
32 | 15/10/2016 | ValidateStudent | Student's eDollar did not check if it is more than 3 decimal places | High | 5 | 10 | 15/11/2016 | None | Haseena | Found while doing javaDocs | Resolved
33 | 2016-10-16 | AddBidServlet | Able to add a bid during inactive round | High | 5 | 5 |  | AddBidTestCase 15 | Cheryl/Huiyan | Function Testing Session
34 | 2016-10-16 | searchSection | Was not able to add decimal bid amount | high | 5 | 10 |  | AddBidTestCase 16 | Cheryl/Huiyan | Function Testing Session
35 | 2016-10-16 | BidController | Bid section limit doesn’t include enrolled sections | high | 5 | 15 |  | AddBidTestCase 17 | Cheryl/Huiyan | Function Testing Session
36 | 2016-10-16 | BidController | Able to bid fro section already enrolled in | High | 5 | 20 |  | AddBidTestCase 18 | Cheryl/Huiyan | Function Testing Session
37 | 2016-10-16 | SearchSection | Shows a blank page when searching for section under course that doesn't contain sections | High | 5 | 25 |  | SearchTestCase 5 | Cheryl/Huiyan | Function Testing Session
Current Bug Point | 25
Total Bug Point | 181
Symbols
= Stop development and begin debug session
= used the planned debugging tme in the iteration
Formula=1 x num (low) + 5 x num (high) + 10 x num (critical)
|  | Severity | Description
|  | Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
|  | High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
|  | Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.

## Iteration4
Iteration 4: 17/10/2016-30/10/2016
Date Found | File | Details | Impact level | Bug Value | Total Score | Date Resolved | No. of Test Cases | Found by? | Note | Status
Formula=1 x num (low) + 5 x num (high) + 10 x num (critical)
| Severity | Description
| Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
| High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
| Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.

## Iteration5
Formula=1 x num (low) + 5 x num (high) + 10 x num (critical)
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.