## Iteration1
Pair Programming Metrics
Task | Planned | Actual | PPI | Status | Score(%) | Action
Create Course Entity | 1 | 0.67 | 149.3% | OK | PPM <= 50 | 1.Re-estimate the tasks in the coming iteration(s) and update the schedule document.
Create Student Entity | 1 | 1.1 | 90.91% | OK |  | 2.Review possible pairing & estimation issues.
Create Bid Entity | 1 | 3.07 | 32.57% | Under-estimated | 50 < PPM <= 150 | No action required.
Validate Student.csv | 2 | 2.63 | 76.05% | OK | 150 < PPM | 1.Re-estimate the tasks in the coming iteration(s) ) and update the schedule document.
Set up Database | 2 | 2.43 | 82.3% | OK |  | 2.Review possible pairing & estimation issues.
Create Section Entity | 1 | 1.17 | 85.47% | OK
Validate Course.csv | 3 | 2.92 | 102.7% | OK
Validate Pre-requisite.csv | 28 | 2.5 | 1120% | Over-estimated
Do Common Validation | 1 | 97% | 103.1% | OK
Validate Session.csv | 3 | 2.3 | 130.4% | OK
Validate Course-Completed.csv | 4 | 4.13 | 96.85% | OK
Validate Bid.csv | 4 | 6.3 | 63.49% | OK
Add student into database - BootstrapDAO | 1 | 1 | 100% | OK
Add course completed into database - BootstrapDAO | 2 | 1.48 | 135.1% | OK
Debug Session | 0.5 | 0.63 | 79.37% | OK
Debug Session - ValidateCourse, Course.java | 0.75 | 0.68 | 110.3% | OK
Unzip Files - Unzip Utility | 2 | 1.95 | 102.6% | OK
Add course into database - BootstrapDAO | 1 | 1.72 | 58.14% | OK

## Iteration 2
Pair Programming Metrics
Task | Planned | Actual | PPI(%) | Status | Score(%) | Action
Reformat Code(Part 1) | 2 | 2.5 | 80% | OK | PPM <= 50 | 1.Re-estimate the tasks in the coming iteration(s) and update the schedule document.
Add section into Database - BootstrapDAO | 0.5 | 0.47 | 106.4% | OK |  | 2.Review possible pairing & estimation issues.
Solve GIT de-synced files | 0.5 | 0.2 | 250% | Over-estimated | 50 < PPM <= 150 | No action required.
Reformat Code(Part 2) | 0.5 | 0.82 | 60.98% | OK | 150 < PPM | 1.Re-estimate the tasks in the coming iteration(s) ) and update the schedule document.
Add Pre-requisite into Database - BootstrapDAO | 0.5 | 0.42 | 119% | OK |  | 2.Review possible pairing & estimation issues.
Add Bid into Database - BootstrapDAO | 0.5 | 0.43 | 116.3% | OK
Upload Utility - Unzip file | 1 | 1.22 | 81.97% | OK
Upload Utility - check if file is valid | 1 | 1.15 | 86.96% | OK
Bootstrap Servlet | 1 | 1.73 | 57.8% | OK
BidDAO | 2.5 | 2.77 | 90.25% | OK
SectionDAO | 2.5 | 1.85 | 135.1% | OK
StudentDAO - retrieve UserId and Password from Database | 0.5 | 0.38 | 131.6% | OK
StudentDAO - methods to retrieve from Database | 2.5 | 2.32 | 107.8% | OK
Login UI | 2 | 1.2 | 166.7% | Over-estimated
StudentController | 2 | 1.27 | 157.5% | Over-estimated

## Iteration 3
Pair Programming Metrics
Task | Planned | Actual | PPI(%) | Status | Score(%) | Action
Login Page - servlet, controller, page | 2.5 | 2.68 | 93.28% | OK | PPM <= 50 | 1.Re-estimate the tasks in the coming iteration(s) and update the schedule document.
CourseDAO | 0.5 | 0.72 | 69.44% | OK |  | 2.Review possible pairing & estimation issues.
CourseSection Controller | 1 | 0.92 | 108.7% | OK | 50 < PPM <= 150 | No action required.
Bootstrap Contoller | 1 | 1.27 | 78.74% | OK | 150 < PPM | 1.Re-estimate the tasks in the coming iteration(s) ) and update the schedule document.
Bid Controller | 3 | 3.3 | 90.91% | OK |  | 2.Review possible pairing & estimation issues.
Debug Bootstrap | 3 | 2.4 | 125% | OK
Add Bid Servlet | 1.5 | 3.47 | 43.23% | Under-estimated
Student view page(populate display:bids, enrolled classes, round info student details) | 3 | 2.33 | 128.8% | OK
Student servlet to take in query from homepage | 3 | 3 | 100% | OK
Admin Homepage-Admin Viewpage(boostrap, start round,end round) | 0.5 | 0.55 | 90.91% | OK
AdminDAO retrieve userid and password | 0.5 | 0.6 | 83.33% | OK
Admin Servlet-Admin servlet to take in query from homepage | 0.5 | 0.42 | 119% | OK
CourseCompleteDAO,SectionStudentDAO | 0.5 | 0.73 | 68.49% | OK
Drop Section Servlet-handle Input from <view> and response from controller | 0.5 | 1.6 | 31.25% | Under-estimated
BidDAO-sql Select stamtent from database to detrmine clearing price for specific section | 1 | 1.23 | 81.3% | OK
Student Servlet-handle update bids | 1 | 1.33 | 75.19% | OK
RoundDAO-Update ROund Status in Databse to started/ended | 0.5 | 0.53 | 94.34% | OK
RoundController calls ROundDAO to update round status to strated/ended | 0.5 | 0.53 | 94.34% | OK
Admin Servlet- takes in start round query, calls roundController method to start/stop | 0.5 | 0.98 | 51.02% | OK
BidDAO- Update Bid status in database | 1 | 1.17 | 85.47% | OK
Search Sections View page | 2.5 | 2.93 | 85.32% | OK
RoundController calls StudentController ,refund unsuccessful bids | 1.5 | 1.58 | 94.94% | OK
Debug- Debug Student Functions | 4 | 4.22 | 94.79% | OK
Debug Deployment | 3 | 2 | 150% | OK
JavaDocs Controller | 1.5 | 1.82 | 82.42% | OK
JavaDocs - DAO | 1.5 | 1.55 | 96.77% | OK
JavaDocs-Entity | 0.5 | 0.8 | 62.5% | OK
Debugging Session | 4 | 4.38 | 91.32% | OK
Split start and stop button | 1 | 1.3 | 76.92% | OK
student view results page | 1 | 1.3 | 76.92% | OK
Update search section page | 1 | 1.37 | 72.99% | OK