## Slide 1: PM Review Wk 7
G2T6
Lim Wai Liang Aloysius
Chen Huiyan
Haseena Banu Binte Ghulam Mohamed
Seah Chen Xun Regan
Lim Wei Lin Cheryl

## Slide 2: Model used: MVC
View
Controller
Model
Servlet
Controller
DAO
Database
JSP Pages
Entity
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 3
Iteration 1
Iteration 2
Entity Coding
Designing
Iteration 3
Bootstrapping
Login
Controller
DAOs
Planned Iterations
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Database Setup
Login UI
Iteration3
Admin Functionality
Clear Rounds
Teaching & Sharing Session
Student Functionality
Bidding
Admin UI
Student UI

## Slide 4
Planned Iterations
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Teaching & Sharing Session
Iteration 5
Iteration 4
Web Service
JSON
UAT Tests
Iteration 6
Project Submission
Buffer Coding Time
UAT Debug

## Slide 5
Iterations timing
Iteration 1
11 September – 25 September (15 days)
26 September – 2 October (7 days)
3 October – 16 October (14 days)
17 October – 30 October (14 days)
31 October – 6 November (7 days)
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
6 November – 20 November (7 days)

## Slide 6
Project Milestones
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Milestone | Week | Project Manager (PM)
Supervisor Meeting 1 | 6 | Aloysius
Project Manager Review | 7 | Aloysius
In Class Review | 9 | Cheryl
Supervisor Meeting 2 | 11 | Huiyan
User Acceptance Test | 12 | Haseena
Project Submission | 13 | Regan
Final Presentation | 14 | Regan

## Slide 7
Project Milestones
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Milestone | Week | Project Manager (PM)
Complete Backend Coding | 7 | Aloysius
Finish Admin Functionality | 8 | Cheryl
Finish Student Functionality | 9 | Cheryl
Finish Web Service Functionality | 11 | Huiyan
Group UAT | 12 | Haseena
Complete Project | 13 | Regan

## Slide 8
General meeting
Teaching / Sharing session
PP Coding
Test Case Creation
Testing
Function Review
Team meeting to discuss what are to be done in the following week
Prior to session, PM will allocate a specific aspect to research on and share findings
Testing of code against corner case and test case. Bugs are to be noted down.
Explanation of code done by PP pairs, and sharing of rational behind coding ideology.
Iteration Format
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 9: Critical path
Entity Coding (2 Days)
Designing
(2 Days)
Bootstrapping
(11 Days)
Database Setup
(1 Day)
Utility Coding (2 Days)
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Iteration 1

## Slide 10: Critical path
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Iteration 2
Buffer Coding TIme
Admin Functionality
Clear Rounds (3 Days)
Student Functionality
Bidding
(7 Days)
Web Service
JSON
UAT Mitigation
Admin UI
Student UI
Login
(1 Day)
Controllers
(4 Days)
DAOs
(3 Days)
Login UI (1 Day)
Debug
(2 Days)

## Slide 11: Critical path
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Iteration 3
Buffer Coding TIme
Admin Functionality
Clear Rounds (3 Days)
Student Functionality
Bidding (7 Days)
Web Service
JSON
UAT Mitigation
Admin UI (2 Days)
Student UI (2 Days)
Debug
(2 Days)

## Slide 12: Critical path
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Iteration 4
Web Service JSON (10 Days)
UAT (1 Day)
Debug
(2 Days)
Iteration 5
Fixing Code From UAT
(6 Days)

## Slide 13: Critical path
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Iteration 6
Buffer Days (7 Days)
Project ends on 13 Nov
Buffer Days: 7 Days
(6 Nov – 12 Nov)
Project Submission
Final Presentation

## Slide 14: bug Metric
Current Progress: Time-Boxing
Validation
Planned
Database
File Upload
Actual
(on 26 Sept)
Test
Iteration 1
Iteration 2
Login
Controller
DAO
Iteration 1
Iteration 2
Validation
Database
File Upload
Test
Test
Login
Controller
DAO
11/09/2016
25/09/2016
02/10/2016

## Slide 15
Iteration Progress
Iteration 1
Designing & Diagramming
Class Diagram
Sequence Diagram
Logical Design
Use Case Design
Entity Classes
Controller
Student.java
Course.java
Section.java
Bid.java
BootstrapController
BootstrapServlet
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 16
Iteration Progress
Iteration 1
Utility Classes
FileUpload
Unzip
ConnectionManager
Validation Classes
StudentValidation
CourseValidation
SectionValidation
BidValidation
Pre-reqValidation CourseCompletedValidation
CommonValidation
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 17: Task Metric
Scheduled Task:
Non Programming : 16
Programming : 25
Actual Completed Task:
Non Programming : 13 / 16
Programming : 15 / 25
Final Score:
Iteration 1
68.29
50 < TM <= 90 | Re-estimate the tasks for the future iterations. Deduct the number of days behind schedule from buffer days. If there is no more buffer day, decide the functionalities to drop.
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Mitigation Taken:
Deducting 1 day from buffer.
Adding one day into Iteration 2.

## Slide 18: bug Metric
SQL create table statements | change NULL to NOT NULL | Low | 1 | 
BootstrapController | change HashMap<String,String> to HashMap<String, ArrayList<String>> for courseComplete | High | 5 | 
BootstrapController | change HashMap<String,String> to HashMap<String, ArrayList<String>> for pre-Req | High | 5 | 
ValidateSection | change input type from ArrayList<String> to ArrayList<Section> | High | 5 | 5
BootstrapController | change SECTIONLIST to Hashmap <String, ArrayList<Section>> | High | 5 | 10
Added Debug Session to Schedule : Bug Metric reached 10. |  |  |  | 
ValidateSection | change SECTIONLIST to STUDENTSECTION | Low | 1 | 1
ValidateSection | line 67: isValidInstructor change to isValidVenue | Low | 1 | 2
ValidateCourse | change return type for isValidDateFormat from boolean to date | Low | 1 | 3
Course | change all datatype for the dates from String to Date | High | 5 | 8
Added Debug Session to Schedule : Bug affected DAO creation |  |  |  | 
File with Bug | Change | Impact | Score | Total
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 19
Iteration 1 roles
Iteration 1
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Project Manager
Regan & Aloysius
Programming Pair 1
Cheryl & Aloysius (Wk 1)
Cheryl & Regan (Wk 2)
Milestone:
Supervisor Meeting
Programming Pair 1 | Cheryl & Aloysius (Wk1) Cheryl & Regan (Wk2)
Programming Pair 2 | Huiyan & Haseena

## Slide 20
Iteration 2 roles
Iteration 2
Project Manager
Aloysius
PM Review
Programming Pair 2 | Regan & Cheryl
Programming Pair 1 | Huiyan & Haseena
Milestone:
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 21
Iteration 3 roles
Iteration 3
Project Manager
Cheryl
In-Class Review
Complete Backend Coding
Programming Pair 2 | Regan & Huiyan
Programming Pair 1 | Aloysius & Haseena
Milestone:
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 22
Iteration 4 roles
Iteration 4
Project Manager
Huiyan
Supervisor Meeting 2
Finish Admin & Student Functionality
Programming Pair 1 | Aloysius & Regan
Programming Pair 2 | Cheryl & Haseena
Milestone:
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 23
Iteration 5 roles
Iteration 5
Project Manager
Haseena
UAT
Finish Web Service Functionality
Programming Pair 1 | Aloysius & Huiyan
Milestone:
Programming Pair 2 | Cheryl & Regan
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 24
Iteration roles
Final Week
Project Manager
Regan
Complete Coding
Final Submission & Presentation
Milestone:
Programming Pair 1 | Haseena & Huiyan
Programming Pair 2 | Aloysius & Cheryl
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure

## Slide 25
Pair Programming Structure
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Leverage on each other’s individual strengths in coding
Objectives
Pair Criteria
Coding Experience
1
2
Schedule
3
Grades
4
Workstyle / Codestyle

## Slide 26
End of Slides

## Slide 27
Buffer Coding TIme
Iteration 1
Iteration 2
Entity Coding
Designing
Iteration 3
Iteration 5
Iteration 4
Bootstrapping
Login
Controller
DAOs
Admin Functionality
Clear Rounds
Student Functionality
Bidding
Web Service
JSON
UAT Mitigation
Planned Iterations
Functionalities
Schedule
Metrics
Roles and Responsibility
Pair Programming Structure
Database Setup
Login UI
Admin UI
Student UI
Teaching & Sharing Session

## Slide 28: Schedule – Critical path – Iteration1
Diagraming
(8 hrs)
Course Entity
(1 hr)
Validation Classes
(22.5 hrs)
Utility Classes
(5 hrs)
Bootstrap DAO
(9 hrs)
Database Setup
(2 hrs)
Section Entity
(1 hr)
Bid Entity
(1 hr)
Student Entity
(1 hr)

## Slide 29: Schedule – Critical path
Bootstrap DAO
(9 hrs)
Bootstrap Controller
(2 hrs)
Test
(2 hrs)
Bootstrap Servlet
(1 hrs)
Debug
(2 hrs)

## Slide 30: Metrics
Task | Planned Hours | Actual Hours | PPM | Action
Create Course Entity | 1 | 0.67 | 1.50 | No action required
Create Student Entity | 1 | 1.1 | 0.91 | No action required
Create Section Entity | 1 | 1.17 | 0.86 | No action required
Validate course.csv | 3 | 2.92 | 1.03 | No action required
Create Bid Entity | 1 | 3.07 | 0.33 | For future task, PM must be informed about the start/end and duration of task before starting.
PPM | Action
0.5-1.5 | No action required
<0.5 | Re-estimate Review issues
>1.5 | Re-estimate Review issues

## Slide 31: Metrics
Task | Planned Hours | Actual Hours | PPM | Action
Validate student.csv | 3.0 | 2.63 | 1.14 | No action required
Setup database | 2 | 2.43 | 0.82 | No action required
Validate Prerequisite.csv | 4 | 2.5 | 1.60 | Re-estimate buffer time for coding sessions (Reduce)
Do common validations for all csv files | 1 | 0.97 | 1.03 | No action required
Validate Section.csv | 3.5 | 2.3 | 1.52 | Re-estimate buffer time for coding sessions (Reduce)
Validate Courses Completed.csv | 4 | 4.13 | 0.97 | No action required

## Slide 32: Roles and Responsibilities
Iteration | Week | Project Manager (PM) | Pairings
1 | 5 - 6 | Regan (PM1) Aloysius (PM2) | Huiyan – Regan Haseena – Huiyan Aloysius – Cheryl
2 | 7 | Aloysius | Regan – Cheryl Haseena – Huiyan Aloysius – Cheryl Regan – Haseena
3 | 8 - 9 | Cheryl | Aloysius – Regan Haseena – Huiyan Cheryl – Regan Cheryl – Huiyan
4 | 10 -11 | Huiyan | Haseena – Cheryl Aloysius – Regan
5 | 12 | Haseena | Aloysius – Cheryl Regan – Huiyan

## Slide 33: Pair Programming Rotation Plan

## Slide 34: JUNK
Iter 1
Iter 2
Iter 3
Iter 4
Iter 5